## Active
ID | Priority | Status | Doctype | Item | Description | Change Date | Comment
23 | 1 - High | hold | all | Product Description Table | The Product Information -> Product Type field is mapped to the wrong element it should be the marketing_catagory from 2.16.840.1.113883.2.20.6.27 but not sure how to encode this. <templateId root="2.16.840.1.113883.2.20.6.27" extension="Biologic"/>
28 | 1 - High | hold | CPID | CPID Overview | Proposed Indication has not been mapped yet
30 | 1 - High | not started | all | General | In all places where there is a substance it should be in the following format "<code@displayName> (ID: <code@code>)" where the < > is replaced with the content
32 | 1 - High | not started | all | Scailing Bar | Now we have 2 different look and feels (the red arrow in the SPM and the scailing bar is different), I like the CPID scale bar better, but missing the collapse/expand red arrow. Please add arrow then copy the code to the SPM and deploy to dev.2
5 | 2 - Medium | not started | all | multiple roles | When an organization has multiple roles the entry should show in all applicable places, currently only the first is displayed
19 | 2 - Medium | not started | all | General | Separate eac entry in repeating fields, using ";" and ensure there are 2 spaces after the ";" see Summary of Product Information/Route Of Administration
18 | 3 - Low | not started | all | General | Footers should be formated as header in all tables
29 | 3 - Low | not started | all | header tab | Font size and bolding is not applied uniformly | 2018-03-08 | Still not correct on my end
23 | 3 - Low | not started | all | Product Description Table | Remove the Product Information -> Reporting Period field
2 | 3 - Low | not started | all | File Names | Rename to hpfb-<doctype>*
3 | 3 - Low | not started | all | header bolding | Bold the labels in the header
6 | 3 - Low | not started | all | header spacing | The Brand Name label has extra spacing before the <value>
8 | 3 - Low | not started | all | Organizations Table | remove the Organizations Table - Business Operations column
9 | 3 - Low | not started | all | Organizations Table | For the DIN Owner add a ID column at the end, the content will be /document/author[1]/assignedEntity[1]/representedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/id[1]/@extension where /document/author[1]/assignedEntity[1]/representedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/id[1]/@root="2.16.840.1.113883.2.20.6.31"
10 | 3 - Low | not started | all | Organizations Table | Replace the content of the ID/FEI column with /document/author[1]/assignedEntity[1]/representedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/id[1]/@extension where /document/author[1]/assignedEntity[1]/representedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/id[1]/@root="2.16.840.1.113883.2.20.6.31"
11 | 3 - Low | not started | all | Organizations Table | Change the label from ID/FEI to Company ID (code)
12 | 3 - Low | not started | cpid | Facilities Table | Clone the Organizations Table but replace the Company ID column with Facility ID where the facility ID content is TBD. It needs to be in the TOC
13 | 3 - Low | not started | all | Organizations Table | remove the Role column
31 | 3 - Low | not started | all | header tab | Add a space before the / in the value part of the Date of Initial Approval/Revision:
33 | 3 - Low | not started | CPID | Bookmarks | not all hyperlinks work

## Closed
ID | Priority | Status | Doctype | Item | Description | Change Date | Comment
7 | Low | Completed | all | header spacing | There needs to be more space before the Brand Name label | 2018-03-07
21 | High | Complete | all | TOC | Create TOC entries for CPID Overview subsections | 2018-03-07
14 | 10 | Complete | CPID | Title Bar | Add 3 spaces after Date of Initial Approval/Revision:
15 | 10 | Complete | CPID | Title Bar | Redce to 3 spaces after Brand Name: Date of Initial Approval/Revision:
16 | 10 | Complete | all | Images | move the HC images to static site
17 | 10 | Complete | CPID | General | reduce size of Summary of Product Information/Strength Field
22 | Medium | not started | all | Product Description Table | The Product Information -> Route Of Administration field needs 2 spaces after each ;
26 | 1 - High | not started | CPID | Canada Logo | Please remove the image
27 | 1 - High | not started |  | CPID Overview | Non-Proprietary Name of Drug Substance, should include the code and be in the following format "<code@displayName> (<code@code>)" where the < > is replaced with the content
4 | 2 - Medium | in progress | cpid | Create xslt | Start Generating the CPID
1 | 1 - High | not started | all | Scailing Bar | Change so that the user can resize by selecting the scailing bar rather than only the leading edge of the bar | 2018-03-07 | Does not work for CPID