## Active
ID | Priority | Status | Doctype | Item | Description | Change Date | Comment
28 | 1 - High | hold | CPID | CPID Overview | Proposed Indication has not been mapped yet
39 | 3 - Low | not started | CPID | Organizations Table | Missing from CPID
18 | 3 - Low | not started | all | General | Footers should be formated as header in all tables
12 | 3 - Low | not started | CPID | Facilities Table | Clone the Organizations Table but replace the Company ID column with Facility ID where the facility ID content is TBD. It needs to be in the TOC
44 | 2 - Medium | not started | all | Product Description Table | The Product Information -> Route Of Administration is not showing the display name from OID 2.16.840.1.113883.2.20.6.7 for all …/manufacturedProduct[1]/consumedIn[1]/substanceAdministration[1]/routeCode[1] elements
45 | 2 - Medium | not started | all | Product Description Table | The Active Ingredient/Active Moiety -> Basis Of Strength is not showing the (Substance ID: <id>) aspect
46 | 2 - Medium | not started | all | Product Description Table | The Product Characteristics -> Value is missing the originalText content, should be in the format <display name> (<original text>) example white (off-white)
47 | 2 - Medium | not started | all | Section Headings General | If a section has a templateId element where the root is 2.16.840.1.113883.2.20.6.55 or 2.16.840.1.113883.2.20.6.56 then add the display name and code in () after the title of the section an example would be Part III: Consumer Information (A Product (1234))
48 | 2 - Medium | not started | all | Product Description Table | Active Ingredient/Active Moiety -> Basis Of Strength, the (Substance ID: <sustance ID>) aspect is missing
49 | 2 - Medium | not started | all | Product Description Table | Active Ingredient/Active Moiety -> Ingredient Name, the Substance name aspect is missing
50 | 2 - Medium | not started | all | Product Description Table | Inactive Ingredients -> Ingredient Name, the Substance name aspect is missing
51 | 2 - Medium | not started | all | Product Description Table | Other Ingredients -> Ingredient Name, the Substance name aspect is missing
52 | 2 - Medium | not started | all | Product Description Table | Marketing Information, take a look at why the fonts size is different

## Closed
ID | Priority | Status | Doctype | Item | Description | Change Date | Comment
1 | 1 - High | not started | all | Scailing Bar | Change so that the user can resize by selecting the scailing bar rather than only the leading edge of the bar | 2018-03-07 | Does not work for CPID
2 | 1 - High | not started | all | File Names | Rename to hpfb-<doctype>*
3 | 3 - Low | not started | all | header bolding | Bold the labels in the header
4 | 2 - Medium | in progress | cpid | Create xslt | Start Generating the CPID
5 | 2 - Medium | hold | all | multiple roles | When an organization has multiple roles the entry should show in all applicable places, currently only the first is displayed
6 | 3 - Low | not started | all | header spacing | The Brand Name label has extra spacing before the <value> |  | Still there in the CPID
7 | Low | Completed | all | header spacing | There needs to be more space before the Brand Name label | 2018-03-07
8 | 3 - Low | not started | all | Organizations Table | remove the Organizations Table - Business Operations column
9 | 3 - Low | not started | all | Organizations Table | For the DIN Owner add a ID column at the end, the content will be /document/author[1]/assignedEntity[1]/representedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/id[1]/@extension where /document/author[1]/assignedEntity[1]/representedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/id[1]/@root="2.16.840.1.113883.2.20.6.31"
10 | 3 - Low | not started | all | Organizations Table | Replace the content of the ID/FEI column with /document/author[1]/assignedEntity[1]/representedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/id[1]/@extension where /document/author[1]/assignedEntity[1]/representedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/id[1]/@root="2.16.840.1.113883.2.20.6.31"
11 | 3 - Low | not started | all | Organizations Table | Change the label from ID/FEI to Company ID (code)
13 | 3 - Low | not started | all | Organizations Table | remove the Role column
14 | 10 | Complete | CPID | Title Bar | Add 3 spaces after Date of Initial Approval/Revision:
15 | 10 | Complete | CPID | Title Bar | Redce to 3 spaces after Brand Name: Date of Initial Approval/Revision:
16 | 10 | Complete | all | Images | move the HC images to static site
17 | 10 | Complete | CPID | General | reduce size of Summary of Product Information/Strength Field
19 | 2 - Medium | not started | all | General | Separate each entry in repeating fields, using ";" and ensure there are 2 spaces after the ";" |  | Also in the SPM header, the Product Description -> Route Of Administration for product 2 etc…
21 | High | Complete | all | TOC | Create TOC entries for CPID Overview subsections | 2018-03-07
22 | Medium | not started | all | Product Description Table | The Product Information -> Route Of Administration field needs 2 spaces after each ;
23 | 1 - High | not started | all | Product Description Table | The Product Information -> Product Type field is mapped to the wrong element it should be the extension attribute from OID 2.16.840.1.113883.2.20.6.53 the xpath is product specific but for product 1 it is /document/component[1]/structuredBody[1]/component[1]/section[1]/subject[1]/manufacturedProduct[1]/manufacturedProduct[1]/templateId[1]
26 | 1 - High | not started | CPID | Canada Logo | Please remove the image
27 | 1 - High | not started |  | CPID Overview | Non-Proprietary Name of Drug Substance, should include the code and be in the following format "<code@displayName> (<code@code>)" where the < > is replaced with the content
29 | 3 - Low | not started | all | header tab | Font size and bolding is not applied uniformly | 2018-03-08 | Still not correct on my end
30 | 1 - High | pending test | all | General | In all places where there is a substance it should be in the following format "<code@displayName> (ID: <code@code>)" where the < > is replaced with the content |  | The SPM still uses the old convention as an example A-105972 (UNII: 9B1B8HD569)
31 | 3 - Low | not started | all | header tab | Add a space before the / in the value part of the Date of Initial Approval/Revision: |  | Still an issue in the SPM
32 | 1 - High | not started | all | Scailing Bar | Now we have 2 different look and feels (the red arrow in the SPM and the scailing bar is different), I like the CPID scale bar better, but missing the collapse/expand red arrow. Please add arrow then copy the code to the SPM and deploy to dev.2
33 | 3 - Low | not started | CPID | Bookmarks | not all hyperlinks work
34 | 2 - Medium | not started | CPID | Summary of Product Information | The displayname value is missing for substance 212WAX8KDD?
34 | 3 - Low | not started | all | Product Description Table | Remove the Product Information -> Reporting Period field
35 | 2 - Medium | not started | all | Product Description Table | The value correscpoding to label 10039 (Item Code (Source)) is incorrect it should be mapped (ignore the [1] in the xpath) /document/component[1]/structuredBody[1]/component[1]/section[1]/subject[1]/manufacturedProduct[1]/manufacturedProduct[1] for the applicable product where codeSystem="2.16.840.1.113883.2.20.6.55, insert MPID: before the value, then use displayName (code)
36 | 1 - High | not started | all | Content HyperLinks | They don’t seem to work anymore, the syntax is right since they work when I use the FDA Stylesheet but not when I use either dev.2 or CPID
37 | 2 - Medium | hold | all | Organizations Table | We are going to restructure all occurances of the org table, please see the manually created table CPID section 2.3.S.2.1.a as a guideline, but lets chat before you make the change
38 | 1 - High | not started | all | Table of Contents | Only add a TOC entry if the target exists
40 | 1 - High | not started | CPID | Product Description Table | Missing from CPID
41 | 2 - Medium | not started | all | Organization | Change role to use /document/author/assignedEntity[1]/representedOrganization[1]/assignedEntity[1]/assignedOrganization[1]/assignedEntity[1]/performance[1]/actDefinition[1]/code where codeSystem="2.16.840.1.113883.2.20.6.33"
42 | 1 - High | not started | all | File Restructure | Rename the entry points to be hpfb-<doctype>.??? Where the <doctype> is either cpid or spm. Move the Product Description Table and the Organization Table to the shared library in the SPL directory. Look at moving all section rendering aspects to shared libraries (generally everything that is not unique should be in the shared library
43 | 2 - Medium | not started | all | Product Description Table | The Product Information - > Product Type is showing the code value (1) not the diplay label (Pharmaceutical)